## Close Calendar
Month-End Close Calendar and Checklist
Business days are counted from the first business day after period end. Adjust the day targets to your own close length.
Business day | Task | Owner | Depends on | Status | Notes
BD 1 | Close the period to new transactions; notify the team |  | —
BD 1 | Import and categorise all bank and card feeds |  | —
BD 1 | Confirm payroll for the period is fully posted |  | —
BD 2 | Reconcile all cash accounts |  | Feeds imported
BD 2 | Reconcile credit cards and merchant clearing |  | Feeds imported
BD 2 | Chase missing receipts and coding questions |  | Categorisation
BD 3 | Invoice all billable work for the period |  | Time approved
BD 3 | Reconcile accounts receivable to the ageing |  | Invoicing complete
BD 3 | Reconcile accounts payable to the ageing |  | Bills entered
BD 4 | Update WIP / unbilled revenue schedule |  | Invoicing complete
BD 4 | Release deferred revenue for the period |  | Contracts reviewed
BD 4 | Post prepaid amortisation and accruals |  | Schedules updated
BD 5 | Post depreciation and amortisation |  | Fixed assets updated
BD 5 | Reconcile payroll liabilities and sales tax |  | Payroll posted
BD 5 | Complete the balance sheet reconciliation checklist |  | All reconciliations
BD 6 | Review P&L against budget and prior period |  | All entries posted
BD 6 | Investigate and document every material variance |  | P&L review
BD 7 | Prepare the monthly reporting package |  | Variance review
BD 7 | Update the cash forecast for actuals |  | Cash reconciled
BD 8 | Internal review of the package |  | Package prepared
BD 8 | Lock the period; no further postings |  | Review complete
BD 9 | Deliver the package and hold the review meeting |  | Period locked
BD 10 | Log close issues and owners for next month |  | Review meeting

## How to use
How to use this calendar
1. 'BD' = business day after period end. BD 1 is the first business day of the new month.
2. The dependency column is the point of the calendar: tasks are ordered so nothing waits on
information that has not been produced yet. Reordering tasks without checking dependencies
is the usual cause of a close that slips.
3. Assign every row an owner by name, not by team. Unowned tasks are what stretch a close.
4. To compress the close, attack the tasks that gate the most dependants first — feeds,
payroll posting and invoicing — rather than the tasks that take longest.
5. Log every issue found after the period is locked and fix the process, not just the number.
This template is general guidance and is not accounting, tax or legal advice.